## Slide 1: Next Steps
Advisory group debrief call
Circulate meeting summary
Identify WG co-chairs to facilitate discussions
Circulate WG participation form so participants can indicate where they want to engage
  People can participate in as many WGs as they wish
Continue outreach to those not here today
  Press release with a call for participation
Set date/time for first WG meetings
  Develop agendas including any carry over items from phase 1
Determine regular schedule of WG virtual meetings

## Slide 2: Rough Timeline
Phase 2 Kickoff meeting (Sept 7, 2017)
Address next steps on prior slide (September 2017)
WG meetings (October – December 2017)
  Discuss new areas and gaps
  Update progress on existing gaps
WG meetings (January – March 2018)
  Develop updated roadmap draft text
Comments on Draft Roadmap Version 2.0 (April 2018)
WG meetings to address comments (May 2018)
Final copy edit / publish Roadmap Version 2.0 (June 2018)
Roadmap Promotion (July – September 2018)

## Slide 3: Questions
Notes: Including on the phone.